Due Diligence Q&A Log

Project Kingfisher - Consolidated Question Register

Date: 31 January 2026 (Extract)

Project Code: WES-PKF-QA-001

VDR Platform: Ansarada

Status: 178 Questions Submitted | 142 Answered | 36 Pending

STRICTLY PRIVATE & CONFIDENTIAL

# Due Diligence Question & Answer Register

This document contains an extract of the Q&A log from the Project Kingfisher Virtual Data Room. Questions have been submitted by Wesfarmers and its advisers through the Ansarada Q&A module.

## Financial Questions (Section 2.0)

| Q# | Question Summary | Submitted By | Status | Response Summary |
| --- | --- | --- | --- | --- |
| F-001 | Monthly revenue by store for FY24 and H1 FY25, by product category | KPMG (FDD) | Answered | Uploaded to VDR Folder 2.05 |
| F-002 | Basis for the $12.8m ATO transfer pricing provision | PwC (Tax) | Answered | ATO Position Paper issued (not formal assessment). Correspondence in Folder 2.10 |
| F-003 | Treatment of $25m vendor loan from Chen Family Trust | KPMG (FDD) | Answered | Interest rate 4.5% p.a. vs benchmark 6.35%. Below-market rate noted |
| F-004 | Earn-Out arrangement mechanics (draft SPA) | Wesfarmers Corp Dev | Pending | Terms under negotiation. Expected w/c 10 Feb |
| F-005 | Reconciliation of management EBITDA to statutory EBITDA | KPMG (FDD) | Answered | Uploaded to Folder 2.03A |
| F-006 | FY25 capex budget by category (maintenance vs growth) | Wesfarmers Corp Dev | Answered | FY25: $82m ($34m maint, $48m growth). Detail in Folder 2.08 |
| F-007 | Accounting treatment for store fit-out costs under AASB 16 | KPMG (FDD) | Answered | Landlord contributions netted against ROU asset. $4.2m in FY24 |
| F-008 | Aged inventory analysis as at 31 December 2025 | KPMG (FDD) | Pending | Data compilation in progress. Expected 5 February |

## Legal & Compliance Questions (Section 3.0)

| Q# | Question Summary | Submitted By | Status | Response Summary |
| --- | --- | --- | --- | --- |
| L-001 | Change of control consents in top 20 supplier agreements | Gilbert + Tobin | Answered | 8 of 20 have CoC provisions. 5 require consent, 3 notification only |
| L-002 | Pending or threatened litigation matters >$500k | Herbert Smith Freehills | Answered | Two matters: customer PI claim ($1.2m, insured) and unfair dismissal ($85k, mediation Feb) |
| L-003 | HOMESTYLE trademark ownership transfer from Singapore entity | Spruson & Ferguson | Pending | Legal advisers reviewing. Response expected w/c 3 February |
| L-004 | Restrictive covenants in founders' employment agreements | Gilbert + Tobin | Answered | 12-month non-compete. Will be superseded by SPA restraint (3yr/5yr) |
| L-005 | Data processing agreements with third-party service providers | Herbert Smith Freehills | Pending | 14 identified, 9 uploaded, 5 being collated |
| L-006 | Modern Slavery Act compliance gap remediation status | EY (ESG) | Answered | 82% Tier 1 assessed (up from 68%). Two Indonesian factories in active remediation |

## Property Questions (Section 4.0)

| Q# | Question Summary | Submitted By | Status | Response Summary |
| --- | --- | --- | --- | --- |
| P-001 | Status of renewal negotiations for 8 holdover leases | Cushman & Wakefield | Answered | 6 in active negotiation. Landlords seeking 10-15% increases |
| P-002 | Environmental site assessments for DC sites | EY (ESG) | Answered | Phase 1 ESAs complete. No contamination. Reports in Folder 4.05 |
| P-003 | Make-good obligations and estimated costs by store | Cushman & Wakefield | Pending | $6.2m aggregate. Store breakdown being prepared |
| P-004 | Related party landlord leases (founder-owned properties) | Gilbert + Tobin | Answered | One: head office (Chen Holdings). At market rent per Knight Frank valuation |

## IT & Technology Questions (Section 6.0)

| Q# | Question Summary | Submitted By | Status | Response Summary |
| --- | --- | --- | --- | --- |
| T-001 | SAP ECC 6.0 customisations - number of custom ABAP objects | Deloitte (IT DD) | Answered | ~340 custom objects, ~120 actively used. Catalogue in Folder 6.03A |
| T-002 | Customer data in loyalty database - classification and encryption | Herbert Smith Freehills | Answered | 2.1m members. AES-256 at rest, TLS 1.3 in transit. AWS Sydney |
| T-003 | Annual IT spend breakdown (run vs change) FY24 and FY25 | Deloitte (IT DD) | Answered | FY24: $28.4m. FY25 budget: $32.1m. Increase from POS and cyber projects |
| T-004 | Penetration test results (last 12 months) | Deloitte (IT DD) | Pending | Aug 2025 by CyberCX. Executive summary being prepared for VDR |