Integration Planning Framework

Project Kingfisher - Day 1 Readiness & 100-Day Plan

Date: January 2026

Project Code: WES-PKF-INT-001

Prepared by: Wesfarmers Integration Management Office

Sponsor: Anthony Gianotti, CFO

STRICTLY PRIVATE & CONFIDENTIAL

# 1. INTEGRATION GOVERNANCE

The integration of Target Co will be managed through a dedicated Integration Management Office (IMO) reporting to the Integration Steering Committee.

| Name | Role | Responsibility |
| --- | --- | --- |
| Anthony Gianotti | Chair (Wesfarmers CFO) | Overall integration oversight and escalation |
| Sarah Mitchell | IMO Director | Day-to-day integration leadership |
| Rachel Wong | Target Co CFO (Retained) | Target-side coordination and business continuity |
| James Thornton | Integration Program Manager | Workstream coordination and reporting |

# 2. INTEGRATION WORKSTREAMS

| # | Workstream | Lead | Key Deliverables | Priority |
| --- | --- | --- | --- | --- |
| 1 | Finance & Reporting | Wesfarmers Group Finance | Chart of accounts alignment, reporting integration | Critical |
| 2 | IT & Systems | Wesfarmers Digital | TSA setup, SAP migration, POS roadmap | Critical |
| 3 | Procurement & Supply Chain | Bunnings Supply Chain | Freight consolidation, supplier rationalisation | High |
| 4 | People & Culture | Wesfarmers People & Culture | Retention execution, org design, cultural alignment | Critical |
| 5 | Legal & Compliance | Wesfarmers Legal | Governance framework, policy rollout | High |
| 6 | Property & Leases | Cushman & Wakefield | Lease renewal strategy, DC optimisation | Medium |
| 7 | Brand & Marketing | HomeStyle Marketing | Brand strategy, loyalty integration | Medium |
| 8 | ESG & Sustainability | Wesfarmers Sustainability | Modern slavery uplift, TCFD reporting | Medium |

# 3. DAY 1 READINESS CHECKLIST

| Category | Item | Owner | Status |
| --- | --- | --- | --- |
| Governance | Board composition confirmed (min. 2 additional independent directors) | Wesfarmers Legal | In Progress |
| Governance | Delegations of authority framework issued | Wesfarmers Legal | Not Started |
| Finance | Bank accounts - signatory changes executed | Group Treasury | In Progress |
| Finance | Intercompany loan repayment ($25m) | Group Finance | Pending Completion |
| Finance | Insurance program transition / novation | Marsh Advisory | In Progress |
| IT | Transition Services Agreement signed | Wesfarmers Digital | Draft in Review |
| IT | Email domain migration plan agreed | Wesfarmers Digital | Not Started |
| People | Retention bonus letters signed (Tier 1) | HR | 6 of 8 Complete |
| People | Day 1 communications pack (all-staff, managers, suppliers) | Comms | Draft Complete |
| Legal | Change of control consents obtained | Gilbert + Tobin | 5 of 8 Complete |
| Legal | HOMESTYLE trademark assignment executed | Spruson & Ferguson | Pending |
| Regulatory | ACCC informal clearance received | Herbert Smith Freehills | Submitted |
| Regulatory | FIRB no-objection notification received | Herbert Smith Freehills | Submitted |

# 4. 100-DAY PLAN SUMMARY

## 4.1 Phase 1: Stabilise (Days 1-30)

Execute retention program and communicate integration approach to all employees, suppliers, and key customers. Implement Wesfarmers governance framework and financial controls. Establish regular reporting cadence. Conduct detailed baseline assessment of all workstreams.

## 4.2 Phase 2: Quick Wins (Days 31-60)

Execute corporate overhead synergies. Commence freight consolidation negotiations. Launch cybersecurity uplift program. Begin SAP S/4HANA migration scoping with selected implementation partner.

## 4.3 Phase 3: Accelerate (Days 61-100)

Present full integration roadmap to Wesfarmers Board. Commence supplier renegotiations for FY27. Finalise property strategy for lease renewals. Launch loyalty program integration feasibility. Deliver first integrated management reporting pack.

# 5. KEY INTEGRATION RISKS

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Key talent attrition | Medium | High | Retention bonuses, clear career paths, cultural autonomy |
| Supplier disruption | Low | High | Proactive engagement, no immediate changes to terms |
| Customer brand confusion | Medium | Medium | Maintain HomeStyle independence, clear comms |
| IT system instability | Medium | High | Phased migration, TSA bridge, extensive UAT |
| Synergy shortfall | Low-Medium | Medium | Conservative base case, dedicated tracking |
| ACCC conditions required | Low | Medium-High | Proactive engagement, prepared divestiture options |