Regulatory & CP Tracker

Project Kingfisher - Status Update

Date: 31 January 2026

Project Code: WES-PKF-REG-002

Prepared by: Herbert Smith Freehills / Wesfarmers Legal

Updated: Weekly (Every Friday)

STRICTLY PRIVATE & CONFIDENTIAL

# 1. CONDITIONS PRECEDENT STATUS

| # | Condition | Responsible | Deadline | Status | RAG |
| --- | --- | --- | --- | --- | --- |
| CP1 | ACCC Informal Clearance | HSF | 30 Apr 2026 | Pre-assessment lodged 20 Jan. Meeting 12 Feb. | Amber |
| CP2 | FIRB No-Objection | HSF | 30 Apr 2026 | Application submitted 22 Jan. Screening expected 30 days. | Green |
| CP3 | No Material Adverse Change | WES Corp Dev | Completion | Monitoring. No MAC events identified. | Green |
| CP4 | Third Party Consents | G+T | Completion | 5 of 8 obtained. 3 outstanding. | Amber |
| CP5 | Key Employee Retention | WES P&C | Completion | 6 of 8 signed. 2 outstanding (CTO, Head of Ecom). | Amber |

# 2. ACCC ENGAGEMENT TIMELINE

| Date | Event | Status |
| --- | --- | --- |
| 20 Jan 2026 | Pre-assessment submission lodged | Complete |
| 27 Jan 2026 | ACCC acknowledged receipt, case team assigned | Complete |
| 12 Feb 2026 | Initial meeting with ACCC Mergers branch | Scheduled |
| Feb-Mar 2026 | ACCC market inquiries | Anticipated |
| Mar 2026 | Preliminary view communicated | Anticipated |
| Apr 2026 | Final decision / clearance letter | Target |

## 2.1 Key Talking Points

- Combined market share 26.5% is well below typical ACCC concentration thresholds

- Bunnings and HomeStyle serve distinct segments with limited substitutability

- Strong competitive constraint from IKEA, Harvey Norman, and online competitors

- No store closures anticipated - acquisition supports growth and investment

# 3. OUTSTANDING THIRD PARTY CONSENTS

| Counterparty | Contract | Type | Status | Risk |
| --- | --- | --- | --- | --- |
| Scentre Group | 11 Westfield leases | Landlord consent | Sent 18 Jan. Meeting 5 Feb. | Low |
| Vicinity Centres | 8 shopping centre leases | Landlord consent | Sent 18 Jan. Awaiting. | Low |
| CBA syndicate | Senior secured facility | Lender consent | Discussion commenced. | Low-Med |

# 4. NEXT STEPS

- Complete ACCC initial meeting (12 Feb) and provide supplementary information

- Follow up outstanding consents (target: all by end March)

- Finalise retention for remaining 2 Tier 1 employees

- Monitor Target monthly financials for MAC assessment

- Brief key customers and suppliers on ACCC talking points